## LI, Junrong
Sprint Tasks (Sprint Backlog) | Week 1 Mar. 27-31 | Week 2 Apr. 3-7 | Week 3 Apr. 10-21 | Week 4 Apr. 24-28 | Week 5 May 1-9
Designing the implementation of List | 2
Designing the implementation of Filter |  | 3
Implementing the filter |  |  | 9
Implementing the list |  |  |  | 10
Writing tests and documentations |  |  |  |  | 8
Total hours | 2 | 3 | 10 | 9 | 8

## WANG, Yanbang
Sprint Tasks (Sprint Backlog) | Week 1 Mar. 27-31 | Week 2 Apr. 3-7 | Week 3 Apr. 10-21 | Week 4 Apr. 24-28 | Week 5 May 1-9
Designing the implementation of SFQ | 3
Designing the implementation of Backend |  | 2
Implementing the SFQ |  |  | 7
Implementing the Backend |  |  |  | 9
Writing tests and documentations |  |  |  |  | 8
Total hours | 3 | 2 | 7 | 9 | 8

## LYU,Shengrui
Sprint Tasks (Sprint Backlog) | Week 1 Mar. 27-31 | Week 2 Apr. 3-7 | Week 3 Apr. 10-21 | Week 4 Apr. 24-28 | Week 5 May 1-9
Designing the implementation of All subject search | 2
Designing the implementation of Timetable |  | 2
Implementing the all subject search |  |  | 8
Implementing the timetable |  |  |  | 8
Writing tests and documentations |  |  |  |  | 8
Total hours | 1 | 2 | 9 | 5 | 10