## LI, Junrong
Sprint Tasks (Sprint Backlog) | Week 1 Mar. 27-31 | Week 2 Apr. 3-7 | Week 3 Apr. 10-21 | Week 4 Apr. 24-28 | Week 5 May 1-9
Designing the implementation of List | 2
Designing the implementation of Filter | 3 | 3
Implementing the filter | 10 | 10 | 10
Implementing the list | 9 | 9 | 9 | 9
Writing tests and documentations | 8 | 8 | 8 | 8
Total hours | 32 | 30 | 27 | 17 | 0

## WANG, Yanbang
Sprint Tasks (Sprint Backlog) | Week 1 Mar. 27-31 | Week 2 Apr. 3-7 | Week 3 Apr. 10-21 | Week 4 Apr. 24-28 | Week 5 May 1-9
Designing the implementation of SFQ | 3
Designing the implementation of Backend | 2 | 2
Implementing the SFQ | 7 | 7 | 7
Implementing the Backend | 9 | 9 | 9 | 9
Writing tests and documentations | 8 | 8 | 8 | 8
Total hours | 29 | 26 | 24 | 17 | 0

## LYU,Shengrui
Sprint Tasks (Sprint Backlog) | Week 1 Mar. 27-31 | Week 2 Apr. 3-7 | Week 3 Apr. 10-21 | Week 4 Apr. 24-28 | Week 5 May 1-9
Designing the implementation of All subject search | 3
Designing the implementation of Timetable | 2 | 2
Implementing the all subject search | 9 | 9 | 10
Implementing the timetable | 8 | 8 | 8 | 8
Writing tests and documentations | 8 | 8 | 8 | 8
Total hours | 30 | 27 | 26 | 16 | 0